## Legend
Legend
Email Marketing
Social Media
Influencer/Collaborator Marketing
Content
PR
Production
Ads
Website

## Workback
Complete By | Category | Task | Who | Status | Notes
| Social Media | Weekly posts in FB Groups - survey, launch questions, looking for x,y,z etc. |  | ONGOING
| Social Media | Finish inviting all contacts to like FB and LinkedIn Pages |  | ONGOING | LinkedIn - 100 credits per month
| E-mail Marketing | Update on Prototypes sent out to Mave & Chez Database
| Ads | Relaunch ads with winning copy with product shots |  |  | $150 ad spend for 2 - 3 week period. CTA: join the pre-sale list
| E-mail Marketing | Update signatures on all emails to include link to pre-sale
| Influencer | Influencer lists almagmated and top 40 selected for initial outreach
| E-mail Marketing | Update on Prototypes sent out to City MOGULS Database
| Collaborator | Template email/IG message created for partner/collaborator outreach |  |  | GOAL: 20 Collaborators/Partners help promote the crowdfunding campaign
| Influencer | Template email/IG message created for influencer outreach |  |  | GOAL: 20 influencers locked in for product shot/video shoot + 5 of Dani/Vic close friends (Pam Fajardo, Nicole Servinis, Oksana Bach...)
| Social Media | IG/Tiktok Content Outline for two months (2 posts per week - 1 reel, 1 image)
| E-mail Marketing | Survey for random population of survey results on Mailchimp
| Ads | Ad Agency for Crowdfunding Campaign secured
| Content | Venue for Video/Product Shot secured
| Content | Ask graphic designer to create all of assets for crowdfunding page and launch
| E-mail Marketing | Update , Crowdfunding, Survey
| Influencer | Reach out and lock in 20 photoshoot participants
| MILESTONE | Pre-Sale List Subscribers: 3000 - 350 VIPs IG Following: 600 TikTok Following: 100
| Website | Launch up-to-date website
| Content | Founder Batch Record 10 Reels for next two months
| Website | Launch Blog with 3 articles |  |  | Dani 1 - Why I'm Slipper Obsessed Vic 2 - Crowdfunding and why we're doing it Nikki 3 - Education on slipper features, why house flats are the best
| E-mail Marketing | Newsletter - Key Features/Survey Reminder
| E-mail Marketing | VIP Blast - Early Bird Specials - expires in 24 hrs |  |  | Your early pledge will help us have the strongest possible launch! CTA: Pledge Now
| E-mail Marketing | NON-VIP Blast - Early Bird Specials - expires in 24 hrs |  |  | 2 hours after VIP Blast Deliver messages at strategic points before and during your campaign using email templates Track real-time pledge performance Identify which subscribers haven't backed your project, then send retargeting emails to encourage them to pledge
| MILESTONE | LAUNCH KICKSTARTER
| MILESTONE | Pre-orders available now for 2nd edition
| MILESTONE | E-commerce store launches to fulfill pre-orders for 2nd edition of slippers coming soon
Crowdfunding Campaign Wraps - push people to
| PR | Press Release/PR Strategy Fall E-commerce Launch
| MILESTONE | Prototypes finalized and samples ordered